## Slide 1: Critical Path Analysis

## Slide 2: Tasks, durations, and dependencies
Task | Effort (person-days) | Duration (days) | Dependencies
T1 | 15 | 10 | 
T2 | 8 | 15 | 
T3 | 20 | 15 | T1 (M1)
T4 | 5 | 10 | 
T5 | 5 | 10 | T2, T4 (M3)
T6 | 10 | 5 | T1, T2 (M4)
T7 | 25 | 20 | T1 (M1)
T8 | 75 | 25 | T4 (M2)
T9 | 10 | 15 | T3, T6 (M5)
T10 | 20 | 15 | T7, T8 (M6)
T11 | 10 | 10 | T9 (M7)
T12 | 20 | 10 | T10, T11 (M8)

## Slide 3: Graph representation of tasks and dependencies

## Slide 4: Activity bar chart

## Slide 5: Critical path analysis
Given task durations and dependencies, critical path analysis computes the earliest time to complete a project.
Outputs of critical path analysis
  Earliest time to completion.
  Critical path(s).
Critical tasks – a set of tasks that, when delayed, will cause the entire project schedule to slip.
Two special critical tasks:
  Start Task – milestone marking the beginning of the project.
  Finish Task – milestone marking the end of the project.
Critical path – a sequence of critical tasks from Start and Finish.

## Slide 6: Calculating the critical path
Initialize
  Start Task’s earliest and latest starting times are set to 0
Forward Pass
  Determine earliest starting times for all tasks beginning with Start Task
  Compute candidate Earliest Times from the Earliest Times of each predecessor plus the duration from the predecessor
  Pick the highest number
Initialize Finish Task
  Finish Task’s Latest Time is set to its computed Earliest Time
Reverse Pass
  Determine latest starting times for all tasks starting from Finish Task
  Computer candidate Latest Times from the Latest Times of each successor minus the duration to the successor
  Pick the lowest number
Critical Path
  The nodes whose Earliest Times = Latest Times

## Slide 7: Tasks, durations, and dependencies
Task | Duration (days) | Depen-dencies | Earliest Start | Successors | Latest Start
S | 0 |  | 0 | T1, T2, T4 | 0
T1 | 10 | S | 0 | T3, T6, T7 | 0
T2 | 15 | S | 0 | T5, T6 | 5
T3 | 15 | T1 | 10 | T9 | 10
T4 | 10 | S | 0 | T5, T8 | 0
T5 | 10 | T2, T4 | 15 | F | 50
T6 | 5 | T1, T2 | 15 | T9 | 20
T7 | 20 | T1 | 10 | T10 | 15
T8 | 25 | T4 | 10 | T10 | 10
T9 | 15 | T3, T6 | 25 | T11 | 25
T10 | 15 | T7, T8 | 35 | T12 | 35
T11 | 10 | T9 | 40 | T12 | 40
T12 | 10 | T10, T11 | 50 | F | 50
F | 0 | T5, T12 | 60 |  | 60
Project duration

## Slide 8: Two critical paths

## Slide 9: Two critical paths